**Project Status Report II**

|  |
| --- |
| Date of Report Issue/Prepared: March 10, 2023 |

Report Prepared By: Lale Mulati

Employer/Organization: Anjana Shah

|  |  |  |
| --- | --- | --- |
| Project Name:  Project Team:  Period Reporting:  Overall Project Health | Rentitus Web App (Home & Office Rental) | |
| W23\_T21 | |
| Start Date: **Feb 04, 2023** | End Date: **Mar 10, 2023** |
| Green (Good) - Yellow (Warning) - Red (Bad) | |

Summary

|  |
| --- |
| **Project Status Summary** |
| Our project is currently 70% complete, and we are focused on developing the admin part of the system. Our team of developers is working hard to ensure that the system is scalable and user-friendly. |

|  |  |
| --- | --- |
| **Accomplishments As Planned** | **Planned but not Accomplished** |
| Main page | Map |
| Host pages & features (include sign-in as Host, Host profile page, Host item list page, Host Rating features) | Customer service Chatbot |
| Guest Pages & features (simplified sign in/sign out, View only restrictions) | Admin |
| Shopping card |  |
| Transaction page |  |

Upcoming Objectives for **Mar 11, 2023, to Mar 31, 2023**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | | **Planned Activities/Tasks for Next Period** | |  |
| Activity/Task | Assigned To  <name/s> | | Duration  <days> | Date |
| Test#3, report issues, reassign the tasks | Lale | | 1 days | Mar.11-Mar.12 |
| Map | Artem | | 7 days | Mar.12-Mar.19 |
| UI/UX update | Abdelaziz | | 5 days | Mar.12- Mar.17 |
| Backend update (transaction page, host item list page) | Artem | | 8 days | Mar.19 – Mar.27 |
| Admin (initial) | Elham | | 10 days | Mar.14- Mar.24 |
| Final Test | Lale, Artem | | 2 days | Mar.27-Mar.29 |

|  |  |  |  |
| --- | --- | --- | --- |
|  | **Milestones for Next Period** | | |
| Milestone (Objective) | | Assigned To | Delivery Date |
| Admin (customer & Sales) | | Elham | Mar.17 |
| Admin (settings) | | Artem | Mar.21 |
| Admin (customer service) | | Lale | Mar.19 |
|  | |  |  |

Managing Issues and Risk

|  |  |  |
| --- | --- | --- |
| **Issues/Problems** | **Resolution Strategy** | **Due Date** |
| Map | Improve with advanced features( include find the item/host from map, and after click redirect to google map). | Mar.19 |
| Transaction | Resolve the reported issues. | Mar.15 |
| Database | Move from Heroku to MongoDB | Mar.12 |
|  |  |  |

|  |  |  |  |
| --- | --- | --- | --- |
| **Upcoming Risks** | **Risk Ranking**  **(Hi, Med, Low)** | **Risk Impact**  **(Hi, Med, Low)** | **Mitigation Strategy** |
| Admin Features | Med | Low | Before system getting crowded, make more progress on Admin Features. |
| Insurance | Hi | Hi | Make proper 3rd party insurance that can convince client and ensure platforms profit. |
| Delivery | Med | Hi | Chose trustworthy delivery company that has low rate of might lost or damaging the goods. |

**NOTE: Attach additional sheets if insufficient space available**